| # Congress Checklist 2026 |  |  |  |
| --- | --- | --- | --- |
| Task | Responsibility | Actions Required | Deadline | Status/Comments |
| Book Date & Director | Main Coordinator | - Book date for next year’s Congress: through NSWBA, immediately after completion of current congress NOTE: start time: Sat 10am & Sun 9:30am - Book Director for Congress |  | - > LP - Done > Jeff Carberry > LP/KT |
| Organise Sponsorship | Publicity Officer | - Discuss with ? |  | - > ??? Thoughts ??? |
| Book Venue | Main Coordinator |  |  | - Done > LP |
| Develop Brochure & Advertise Event | President, Main Coordinator & Publicity Officer | - Develop brochure: Incl. NSWBA requirements - Make brochure available to NSWBA & Local Members - Advertise on website/Facebook/NSW Bridge Clubs |  | - Done > LP - > - > |
| Organise Spare Players | Main Coordinator | - Spare pair required for standby on Saturday - Spare team required for standby on Sunday |  | - > LP - > LP |
| Setting up Venue prior to Event | Main Coordinator | - Arrange for hall availability for Friday night - Arrange for helpers to assist venue set-up - Need a Ute or trailer - Arrange helpers to assist with removing equipment at end |  | - Done > LP - > LP/Team - > - > LP/Team |
| Catering | Catering Committee | - Book caterers - Coordinate number of sandwiches required ensuring any dietary requirements are considered - Organise expected time for lunch on each day. |  | - Done > LP - > LP - > LP |
| Morning/Afternoon Tea | Catering Committee | - Organise volunteers to provide enough cakes, slices and or biscuits for participants during both days |  | - > |
| Identify Equipment Required and Logistics | Main Coordinator | - Arrange Director’s assistant(s) - Required items: - Tables - Boards - Bridgemates - Table numbers - North Sign - Projector - Microphone - Extension cords/power boards - Bidding Pads only (do not need blocks) - Pens - System cards - blank - Whiteboard - Scissors - Sticky tape - First Aid Kit - Marker Pens - Waste paper bins - Side Tables - Table cloths - Hand sanitiser |  | - Not required - > LP/Team - Not required - Not required - Not required - Not required - Check - Check - > LP - > Team - > LP - > LP - > Team - > Team - > Team - > Team - > Team - > LP/Team - > LP/Team - > Team - > Team |
| Prizes | Treasurer | - Ensure prizes are in envelopes for presentation: both days |  | - > Treasurer |
| Pay any outgoing expenses as per invoices | Treasurer |  |  | - > Treasurer |
| Appeals Committee | Main coordinator | - Fill positions with personnel on each day |  | - KT |
| Arrange for Urns & Buckets | Catering Committee | - Two urns will be required on each day - Arrange for volunteers to refill urns both days - Arrange for at least 4 buckets |  | - Not Required - Not Required - Not Required |
| Arrange for old rags etc… for spillages | Catering Committee | - Ensure plenty of rags or towels are available to mop up any spillages on each day |  | - Not required |
| Purchase required items | Catering Committee | - Identify items required on the days and purchase additional supplies required |  | - > LP |
| Catering Team | Catering Committee | - Organise volunteers to assist in the kitchen on both days: plating up morning teas, lunch & afternoon teas |  | - Not Required |
| Publicity | Publicity Officer | - Arrange photographer for the two days - Take photos on each day of the winners, noting their names - Prepare article for FB & Webpage - Update FB & Webpage with results |  | - > JR - > JR - > JR - > JR |
| Reconcile entries and monies received | Treasurer | - Ensure all payments are received - Ensure partial entry refund for members - Identify best local Pairs and Teams eligibility |  | - > LP - Not required - > LP/KT |